## Read Me
Read Me |  |  | Derived qa view
Baseline |  |  | pilot-0.1-unaccepted
Navigation |  |  | Return to Read Me
Namespace | Record Type | Record ID | Guidance | Feedback
pilot-checklist | guidance | authority | Markdown and declared engine sources are canonical. This is a derived audience view.
pilot-checklist | guidance | feedback | Edit/comment for review; compare the returned workbook against the original XLSX and JSON baseline. Feedback never applies source changes or approvals.
pilot-checklist | guidance | freshness | Check every source-manifest hash before relying on currentness. Preserve annotated workbooks and generate a new export.

## Control
Control |  |  | Derived qa view
Baseline |  |  | pilot-0.1-unaccepted
Navigation |  |  | Return to Read Me
Namespace | Record Type | Record ID | Value | Feedback
pilot-checklist | control | export_id | EXPORT-8d2b056303804a12b44b3698cd955e0a
pilot-checklist | control | contract_version | 0.1
pilot-checklist | control | profile_version | 0.1
pilot-checklist | control | audience | qa
pilot-checklist | control | baseline_revision | pilot-0.1-unaccepted
pilot-checklist | control | generated_utc | 2026-09-26T14:59:15.644515+00:00
pilot-checklist | control | omitted_detail | ADR Source Sections; ADRs; Design Views; Guidance and Handover; Implementation Tasks; Milestones; Roadmap; Source Manifest; UX and Contracts; Full narrative: use complete Markdown source links
pilot-checklist | control | source_validation | structural integrity only; no review, execution or approval granted
pilot-checklist | control | document:DOC-REQ | requirements.md ¦ draft ¦ review controlled synthetic pilot
pilot-checklist | control | document:DOC-DESIGN | design.md ¦ draft ¦ review controlled synthetic pilot
pilot-checklist | control | document:DOC-PLAN | plan.md ¦ draft ¦ review controlled synthetic pilot
pilot-checklist | control | document:DOC-RELEASE | release.md ¦ draft ¦ review controlled synthetic pilot

## Source Manifest
Source Manifest |  |  | Derived qa view
Baseline |  |  | pilot-0.1-unaccepted
Navigation |  |  | Return to Read Me
Namespace | Record Type | Record ID | Source Document | Authority | SHA-256 | Declared Source Revision | Baseline Revision | Feedback
pilot-checklist | source_file | brief.md | brief.md | Authored Markdown | e7764b6a4c70bd76b27dcab48902fdafe8cb9e40f14ded01678588cb1fa5ade9 | pilot-0.1 | pilot-0.1-unaccepted
pilot-checklist | source_file | catalogue.json | catalogue.json | Machine source | 6d275a938bf00ed83c20b2926dff58fc9248d39168e320c0ca68facd9bdc8479 | fixture-0.1 | pilot-0.1-unaccepted
pilot-checklist | source_file | catalogue.schema.json | catalogue.schema.json | Machine source | 8e06fa19a78185e365fd5bc3fbc6566a6954d0813c19bc583adfe812e102bf46 | candidate-0.1 | pilot-0.1-unaccepted
pilot-checklist | source_file | design.md | design.md | Authored Markdown | 984f43be167a81a571a0f895d4a2ef257b0a4604482ec1353c39ed65a2c3402b | 0.1 | pilot-0.1-unaccepted
pilot-checklist | source_file | plan.md | plan.md | Authored Markdown | 96a467cf536e0efa5be4c46966fe3541956a860de7b538edd59912a1f257680a | 0.1 | pilot-0.1-unaccepted
pilot-checklist | source_file | release.md | release.md | Authored Markdown | 5512c49a81d5fd494a80b862c278616b5b3f2d3f16345bbb2179e9211f4f08c4 | 0.1 | pilot-0.1-unaccepted
pilot-checklist | source_file | requirements.md | requirements.md | Authored Markdown | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97 | 0.1 | pilot-0.1-unaccepted

## Readiness and Blockers
Readiness and Blockers |  |  | Derived qa view
Baseline |  |  | pilot-0.1-unaccepted
Navigation |  |  | Return to Read Me
Namespace | Record Type | Record ID | Known State / Limit | Source Document | Feedback
pilot-checklist | limit | DOC-REQ | Document status: draft; source/export validation is not approval. | requirements.md
pilot-checklist | limit | DOC-DESIGN | Document status: draft; source/export validation is not approval. | design.md
pilot-checklist | limit | DOC-PLAN | Document status: draft; source/export validation is not approval. | plan.md
pilot-checklist | limit | DOC-RELEASE | Document status: draft; source/export validation is not approval. | release.md
pilot-checklist | test_run | Test Runs:RUN-01 | Run ID: RUN-01 ¦ Test ID: TC-01 ¦ Result: Not run ¦ Actual Observation: No reader prototype ¦ Revision: unconfirmed ¦ Environment: unconfirmed | requirements.md
pilot-checklist | test_run | Test Runs:RUN-02 | Run ID: RUN-02 ¦ Test ID: TC-02 ¦ Result: Blocked ¦ Actual Observation: No prototype or assistive test environment ¦ Revision: unconfirmed ¦ Environment: unconfirmed | requirements.md
pilot-checklist | test_run | Test Runs:RUN-03 | Run ID: RUN-03 ¦ Test ID: TC-03 ¦ Result: Not run ¦ Actual Observation: No reader prototype ¦ Revision: unconfirmed ¦ Environment: unconfirmed | requirements.md
pilot-checklist | risk | Risks and Decisions:RISK-01 | Item ID: RISK-01 ¦ Type: blocker ¦ Uncertainty / Decision Needed: No implemented reader, observed product tests, support owner or recovery evidence ¦ Impact: Cannot claim ready, published, deployed or accepted release ¦ Mitigation / Options: Obtain actual candidate, product evidence and scoped authority separately ¦ Trigger / Horizon: Before release review ¦ Owner: unconfirmed ¦ Status: open | plan.md
pilot-checklist | risk | Risks and Decisions:RISK-02 | Item ID: RISK-02 ¦ Type: decision ¦ Uncertainty / Decision Needed: Catalogue workload and performance threshold unknown ¦ Impact: Full-file design may need revision ¦ Mitigation / Options: Measure representative workload and agree threshold; retain decision history ¦ Trigger / Horizon: Before extending scenario ¦ Owner: unconfirmed ¦ Status: open | plan.md
pilot-checklist | release | Release Plan:REL-01 | Release ID: REL-01 ¦ Scope Baseline: Proposed REQ-01 through REQ-03; MILE-01, not accepted ¦ Version Scheme: Numbered pilot iteration; not SemVer ¦ Candidate Revision: unconfirmed ¦ Target / Environment: Local fictional scenario; actual recipient environment unconfirmed ¦ Readiness Gates: TC-01/03 Not run; TC-02 Blocked; ADR Proposed; support/recovery unconfirmed ¦ Rollout: Plan only: bounded recipient trial after real review; no execution ¦ Recovery: Proposed: retain source/previous candidate; stop on input modification or misleading error; restore procedure untested ¦ Support / Owner: unconfirmed ¦ Status: planned | release.md

## Artifact Register
Artifact Register |  |  | Derived qa view
Baseline |  |  | pilot-0.1-unaccepted
Navigation |  |  | Return to Read Me
Namespace | Record Type | Record ID | Artifact ID | Type | Title | Status | Owner | Markdown Path | Source Section | Source Revision | Source SHA-256 | Source Authority | Supersedes ID | Machine Source Link | Source Document | Source Section | Source Revision | Source Hash | Feedback
pilot-checklist | document | DOC-REQ | DOC-REQ | document | Reader need and criteria | draft | unconfirmed | requirements.md | context | 0.1 |  | Authored Markdown |  |  | requirements.md | register | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97
pilot-checklist | document | DOC-DESIGN | DOC-DESIGN | document | Proposed input boundary | draft | unconfirmed | design.md | context | 0.1 |  | Authored Markdown |  |  | requirements.md | register | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97
pilot-checklist | document | DOC-PLAN | DOC-PLAN | document | Outcome and learning plan | draft | unconfirmed | plan.md | context | 0.1 |  | Authored Markdown |  |  | requirements.md | register | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97
pilot-checklist | document | DOC-RELEASE | DOC-RELEASE | document | Release gaps and adoption | draft | unconfirmed | release.md | context | 0.1 |  | Authored Markdown |  |  | requirements.md | register | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97
pilot-checklist | contract | CONTRACT-CATALOGUE | CONTRACT-CATALOGUE | contract | Candidate catalogue schema | draft | unconfirmed | design.md | contracts | candidate-0.1 | 8e06fa19a78185e365fd5bc3fbc6566a6954d0813c19bc583adfe812e102bf46 | Machine source |  | catalogue.schema.json | requirements.md | register | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97

## Sources
Sources |  |  | Derived qa view
Baseline |  |  | pilot-0.1-unaccepted
Navigation |  |  | Return to Read Me
Namespace | Record Type | Record ID | Source ID | Publisher / Owner | URI / Path | Edition / Revision | Inspected Date | Supported Claim | Limitations | Source Document | Source Section | Source Revision | Source Hash | Feedback
pilot-checklist | source | SRC-BRIEF | SRC-BRIEF | synthetic scenario author | brief.md | pilot-0.1 | 2026-09-26; authored seed | Read-only exact category lookup and explicit errors | Fictional intent; no stakeholder agreement | requirements.md | sources | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97
pilot-checklist | source | SRC-CONTRACT | SRC-CONTRACT | synthetic contract author | catalogue.schema.json | candidate-0.1 | 2026-09-26; local file | Proposed object fields | No accepted interface or implementation | requirements.md | sources | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97

## Requirements
Requirements |  |  | Derived qa view
Baseline |  |  | pilot-0.1-unaccepted
Navigation |  |  | Return to Read Me
Namespace | Record Type | Record ID | Requirement ID | Class | Statement | Rationale | Source ID | Proposed Priority | Agreed Priority | Decision Evidence | Owner | Status | Source Document | Source Section | Source Revision | Source Hash | Feedback
pilot-checklist | requirement | REQ-01 | REQ-01 | Stakeholder | A reader can list items for an exact case-sensitive category. | Locate relevant checklist items. | SRC-BRIEF | proposed high | unconfirmed |  | unconfirmed | draft | requirements.md | requirements | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97
pilot-checklist | requirement | REQ-02 | REQ-02 | Solution | Empty matches and malformed input produce distinct explanatory states with no partial malformed list. | Avoid confusing absence with parse failure. | SRC-BRIEF | proposed high | unconfirmed |  | unconfirmed | draft | requirements.md | requirements | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97
pilot-checklist | requirement | REQ-03 | REQ-03 | Solution | Opening and filtering a catalogue leave its input bytes unchanged. | Preserve the supplied checklist. | SRC-BRIEF | proposed high | unconfirmed |  | unconfirmed | draft | requirements.md | requirements | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97

## Stories
Stories |  |  | Derived qa view
Baseline |  |  | pilot-0.1-unaccepted
Navigation |  |  | Return to Read Me
Namespace | Record Type | Record ID | Story ID | Actor | Goal | Benefit | Conversation / Scope | Dependency IDs | Estimate / Basis | Owner | Status | Source Document | Source Section | Source Revision | Source Hash | Feedback
pilot-checklist | story | STORY-01 | STORY-01 | checklist reader | locate items in a category | I can focus on the relevant checklist | Exact category; empty/error handling; no editing or authentication. | REQ-01; REQ-02; REQ-03 | unconfirmed | unconfirmed | draft | requirements.md | stories | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97

## Acceptance
Acceptance |  |  | Derived qa view
Baseline |  |  | pilot-0.1-unaccepted
Navigation |  |  | Return to Read Me
Namespace | Record Type | Record ID | Criterion ID | Context | Event | Expected Outcome | Measure / Threshold | Verification Method | Source Artifact ID | Owner | Source Document | Source Section | Source Revision | Source Hash | Feedback
pilot-checklist | criterion | AC-01 | AC-01 | Catalogue has category review and category planning | Reader filters review | Only ITEM-01 is shown; stable item ID and title are visible | Exact case-sensitive match; whitespace handling not yet explicit | Fixture-driven functional test plus actual user walkthrough | STORY-01 | unconfirmed | requirements.md | acceptance | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97
pilot-checklist | criterion | AC-02 | AC-02 | One valid empty-match input and one malformed input are supplied | Reader opens/filters each input | No matches shows No items in this category; malformed input shows Cannot read checklist with no partial list | Two distinct states; keyboard focus and assistive announcements need observation | Error/empty-state tests and keyboard/screen-reader review | REQ-02 | unconfirmed | requirements.md | acceptance | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97
pilot-checklist | criterion | AC-03 | AC-03 | An input-byte hash is recorded before opening | Reader opens and filters the catalogue | After closing, input-byte hash is identical | Byte identity; no silent save | Before/after hash comparison in a selected runtime | REQ-03 | unconfirmed | requirements.md | acceptance | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97

## Test Cases
Test Cases |  |  | Derived qa view
Baseline |  |  | pilot-0.1-unaccepted
Navigation |  |  | Return to Read Me
Namespace | Record Type | Record ID | Test ID | Criterion ID | Preconditions | Steps | Expected Result | Method / Test Source | Owner | Source Document | Source Section | Source Revision | Source Hash | Feedback
pilot-checklist | test_case | TC-01 | TC-01 | AC-01 | Reader prototype and runtime selected | Open catalogue.json; filter review; inspect item IDs/titles | Only ITEM-01; exact match semantics | Planned fixture check; no implementation | unconfirmed | requirements.md | test-cases | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97
pilot-checklist | test_case | TC-02 | TC-02 | AC-02 | Prototype, invalid input and accessibility environment selected | Exercise unmatched category then invalid JSON; inspect states/focus | Distinct empty/error state; no partial malformed list | Planned behavior and assistive walkthrough | unconfirmed | requirements.md | test-cases | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97
pilot-checklist | test_case | TC-03 | TC-03 | AC-03 | Prototype exists; local source file can be hashed | Hash input; open/filter/close; hash again | Hashes identical | Planned file-integrity observation | unconfirmed | requirements.md | test-cases | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97

## Test Runs
Test Runs |  |  | Derived qa view
Baseline |  |  | pilot-0.1-unaccepted
Navigation |  |  | Return to Read Me
Namespace | Record Type | Record ID | Run ID | Test ID | Result | Actual Observation | Revision | Environment | Executed UTC | Executor | Evidence ID | Source Document | Source Section | Source Revision | Source Hash | Feedback
pilot-checklist | test_run | RUN-01 | RUN-01 | TC-01 | Not run | No reader prototype | unconfirmed | unconfirmed |  |  |  | requirements.md | test-runs | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97
pilot-checklist | test_run | RUN-02 | RUN-02 | TC-02 | Blocked | No prototype or assistive test environment | unconfirmed | unconfirmed |  |  |  | requirements.md | test-runs | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97
pilot-checklist | test_run | RUN-03 | RUN-03 | TC-03 | Not run | No reader prototype | unconfirmed | unconfirmed |  |  |  | requirements.md | test-runs | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97

## Links
Links |  |  | Derived qa view
Baseline |  |  | pilot-0.1-unaccepted
Navigation |  |  | Return to Read Me
Namespace | Record Type | Record ID | Link ID | From Namespace | From Type | From ID | Relation | To Namespace | To Type | To ID | Rationale | Source Document | Source Section | Source Revision | Source Hash | Feedback
pilot-checklist | link | LINK-NEED-1 | LINK-NEED-1 | pilot-checklist | requirement | REQ-01 | derived_from | pilot-checklist | source | SRC-BRIEF | Scenario intent | requirements.md | links | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97
pilot-checklist | link | LINK-CASE-1 | LINK-CASE-1 | pilot-checklist | test_case | TC-01 | verifies | pilot-checklist | criterion | AC-01 | Defined case; not an observed result | requirements.md | links | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97
pilot-checklist | link | LINK-NEED-2 | LINK-NEED-2 | pilot-checklist | requirement | REQ-02 | derived_from | pilot-checklist | source | SRC-BRIEF | Scenario intent | requirements.md | links | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97
pilot-checklist | link | LINK-CASE-2 | LINK-CASE-2 | pilot-checklist | test_case | TC-02 | verifies | pilot-checklist | criterion | AC-02 | Defined case; not an observed result | requirements.md | links | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97
pilot-checklist | link | LINK-NEED-3 | LINK-NEED-3 | pilot-checklist | requirement | REQ-03 | derived_from | pilot-checklist | source | SRC-BRIEF | Scenario intent | requirements.md | links | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97
pilot-checklist | link | LINK-CASE-3 | LINK-CASE-3 | pilot-checklist | test_case | TC-03 | verifies | pilot-checklist | criterion | AC-03 | Defined case; not an observed result | requirements.md | links | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97
pilot-checklist | link | LINK-STORY | LINK-STORY | pilot-checklist | story | STORY-01 | satisfies | pilot-checklist | requirement | REQ-01 | Reader outcome | requirements.md | links | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97
pilot-checklist | link | LINK-ADR | LINK-ADR | pilot-checklist | adr | ADR-01 | refers_to | pilot-checklist | requirement | REQ-03 | Design considers read-only boundary | requirements.md | links | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97
pilot-checklist | link | LINK-MILE | LINK-MILE | pilot-checklist | milestone | MILE-01 | refers_to | pilot-checklist | outcome | OUT-01 | Learning output | requirements.md | links | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97
pilot-checklist | link | LINK-RELEASE | LINK-RELEASE | pilot-checklist | release | REL-01 | depends_on | pilot-checklist | milestone | MILE-01 | Evidence before release | requirements.md | links | 0.1 | c95d03feeb17abd558286b94fca6033c61421bf67d43a1f50e2304b123b9fe97

## Risks and Decisions
Risks and Decisions |  |  | Derived qa view
Baseline |  |  | pilot-0.1-unaccepted
Navigation |  |  | Return to Read Me
Namespace | Record Type | Record ID | Item ID | Type | Uncertainty / Decision Needed | Impact | Mitigation / Options | Trigger / Horizon | Owner | Status | Evidence ID | Source Document | Source Section | Source Revision | Source Hash | Feedback
pilot-checklist | risk | RISK-01 | RISK-01 | blocker | No implemented reader, observed product tests, support owner or recovery evidence | Cannot claim ready, published, deployed or accepted release | Obtain actual candidate, product evidence and scoped authority separately | Before release review | unconfirmed | open |  | plan.md | risks | 0.1 | 96a467cf536e0efa5be4c46966fe3541956a860de7b538edd59912a1f257680a
pilot-checklist | risk | RISK-02 | RISK-02 | decision | Catalogue workload and performance threshold unknown | Full-file design may need revision | Measure representative workload and agree threshold; retain decision history | Before extending scenario | unconfirmed | open |  | plan.md | risks | 0.1 | 96a467cf536e0efa5be4c46966fe3541956a860de7b538edd59912a1f257680a

## Release Plan
Release Plan |  |  | Derived qa view
Baseline |  |  | pilot-0.1-unaccepted
Navigation |  |  | Return to Read Me
Namespace | Record Type | Record ID | Release ID | Scope Baseline | Version Scheme | Candidate Revision | Target / Environment | Readiness Gates | Rollout | Recovery | Support / Owner | Status | Source Document | Source Section | Source Revision | Source Hash | Feedback
pilot-checklist | release | REL-01 | REL-01 | Proposed REQ-01 through REQ-03; MILE-01, not accepted | Numbered pilot iteration; not SemVer | unconfirmed | Local fictional scenario; actual recipient environment unconfirmed | TC-01/03 Not run; TC-02 Blocked; ADR Proposed; support/recovery unconfirmed | Plan only: bounded recipient trial after real review; no execution | Proposed: retain source/previous candidate; stop on input modification or misleading error; restore procedure untested | unconfirmed | planned | release.md | release-plan | 0.1 | 5512c49a81d5fd494a80b862c278616b5b3f2d3f16345bbb2179e9211f4f08c4